## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Planning Phase | 11 days | 05 January 2015 8:00 AM | 19 January 2015 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Assign launch team numbers | 1 day | 05 January 2015 8:00 AM | 05 January 2015 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Design and order marketing meterial | 2 wks | 06 January 2015 8:00 AM | 19 January 2015 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Planning complete! | 0 days | 19 January 2015 5:00 PM | 19 January 2015 5:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Public Launch Phase | 11 days? | 20 January 2015 8:00 AM | 03 February 2015 5:00 PM | 1 | 1
6 | Yes | Auto Scheduled | Distribute advance copies | 2 days | 20 January 2015 8:00 AM | 21 January 2015 5:00 PM |  | 2 | Get recipient list from publicist.
7 | Yes | Auto Scheduled | Coordinate megazine feature articles | 7 days | 22 January 2015 8:00 AM | 30 January 2015 5:00 PM | 6 | 2
8 | Yes | Auto Scheduled | Launch public web portal for book | 1 day | 02 February 2015 8:00 AM | 02 February 2015 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Launch social media programs for book | 1 day? | 03 February 2015 8:00 AM | 03 February 2015 5:00 PM | 8 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units